## Alternatives
alternative | description | primary_scope | hydraulic_result_25yr | construction_cost_usd | contingency_percent | total_budget_basis_usd | full_closure_days | easement_status | permit_readiness | outfall_in_channel_work | owner_preference | mandatory_screen_result | screen_note
A | Upsize P-3 and P-4 to 36-inch RCP | Replace 364 ft pipe and reconstruct CB-3 throat | Passes pipe capacity and HGL after replacement | 575000 | 0.15 | 661250 | 7 | Within ROW | Ready | No | High | FAIL | Fails budget and closure cap.
B | Clean and line existing P-2/P-3/P-4 | Jet clean, CCTV, CIPP lining | Fails HGL at CB-3; limited capacity gain | 246000 | 0.12 | 275520 | 2 | Within ROW | Ready | No | Medium | FAIL | Fails hydraulic adequacy.
C | Detention basin with outfall apron work | Construct upstream detention and modify Willow Branch apron | Passes after storage; culvert tailwater unresolved | 492000 | 0.15 | 565800 | 4 | Easement pending | Permit pending | Yes | Medium | FAIL | Fails easement and permit readiness.
D | Targeted P-3 replacement and CB-3 inlet upgrade | Replace P-3 with 30-inch RCP, rebuild CB-3 throat, clean P-4 and outfall | Passes pipe capacity; culvert screening conditional on tailwater verification | 438000 | 0.12 | 490560 | 5 | Within ROW | Ready with tailwater open item | Yes | High | CONDITIONAL | Meets budget and closure; final design requires tailwater confirmation.

## Unit_Cost_Detail
alternative | bid_item | quantity | unit | unit_cost_usd | line_total_usd | source | risk_note | included_in_base_cost
A | 36-inch RCP installed | 364 | lf | 850 | 309400 | Estimator quote EQ-26-OMR-A | Deep utility conflict allowance excluded. | 1
A | CB-3 reconstruction | 1 | ea | 64000 | 64000 | County bid tab average | Requires full closure. | 1
A | Traffic control | 7 | day | 8400 | 58800 | Traffic control schedule | Exceeds closure cap. | 1
B | Jet cleaning and CCTV | 498 | lf | 32 | 15936 | Maintenance contract | Does not restore capacity enough. | 1
B | CIPP lining | 498 | lf | 420 | 209160 | Vendor budget quote | Lining reduces effective diameter. | 1
C | Detention excavation | 4350 | cy | 48 | 208800 | Estimator quote EQ-26-OMR-C | Requires private easement. | 1
C | Outlet control structure | 1 | ea | 78000 | 78000 | Estimator quote EQ-26-OMR-C | Permit pending. | 1
D | 30-inch RCP P-3 replacement | 200 | lf | 640 | 128000 | Estimator quote EQ-26-OMR-D | Fits 5-day closure with double crew. | 1
D | CB-3 throat reconstruction | 1 | ea | 52500 | 52500 | Estimator quote EQ-26-OMR-D | Addresses sag inlet control. | 1
D | P-4 cleaning and outfall debris removal | 222 | lf | 95 | 21090 | Maintenance and environmental pre-check | Tailwater verification remains open. | 1